## Slide 1: SkyWay Renewal
WebCore TU
Notes: Project name – pick a cool sounding name for your project
Sponsors – list your project sponsors here (the people with the money)
Putting your sponsors name boldly out there for all to see is a great way to get their engagement and attention (necessary for any successful project).

## Slide 2: Why are we here?
To revamp the SkyWay website to a fresh and appealing design
To present all relevant information in a clear and understandable system/hierarchy
To revamp the SkyWay website
to a fresh and appealing design
Notes: Write down all the reasons why your company would want to spend money on this project in the first place.
Then pick and highlight the most important one.

## Slide 3: The elevator pitch
For developers and users
who are interested in real-time web communication.
The NEW SkyWay website
is a website
that presents the benefits and features of SkyWay.
Unlike other websites
our project will be a new website for SkyWay.

## Slide 4: Product box
NEW! SkyWay Website
SkyWay, but newer.
New Design!
New Features!
New Colours!
Notes: If you could walk into a store, and buy the shrink wrapped version of your software, what the design of the box look like and what would it say?
Point here is to get your team looking at your project through the eyes of your end customer.

## Slide 5: The NOT list
IN | OUT
Examination of current situation (Design and site stats) | Creating websites other than SkyWay’s.
Establish SkyWay & WebCore aims | 
Examination of Competitors/Related Sites | 
User Story Mapping | 
Paper prototyping | 
UNRESOLVED
Which frameworks/technologies to use
COLOURS!
Notes: List all the big ticket items you are (and are NOT) going to deliver within the scope of this project.
Before starting your project move all the UNRESOLVED ones to either IN or OUT.

## Slide 6: Your project community
Ewan
Customer Companies
NTT Com
WebCore
Everyone else !
... is always bigger than you think!
大津谷
Independent Developers
Notes: List everyone you are going to have to interact with at some point during the course of your project.
Goal is to start building relationships with these people and let them know we are coming down the tracks (before we actually get there).

## Slide 7: Technical solution
Danger!
Out of scope
Technologies:
HTML, CSS, JS
JQuery, Bootstrap
GitHub pages, Jekyll?
Photoshop, Sketch
GitHub
Other?
Internet
Notes: This is about letting people know how we plan on building this thing.
If there are any tools or libraries assumptions you are making list them here.
Also if there are areas of the application architecture that are risky highlight those too.

## Slide 8: What keeps us up at night
That the design process takes much longer than expected (unforeseen difficulties)
The new site is less popular than the current version
Notes: This is your chance to call out any craziness you’ve heard while building the deck, and having a frank conversation with your sponsors and your team about how you are going to handle it.
This is perhaps on of the most powerful slides in the deck – it’s your chance to ask for whatever you need to be successful and the consequences if you don’t get it.
Use it!

## Slide 9: The A-Team
# | Role | Competencies/Expectations
1 | Ewan | Interest in UI/UX Design Coding Experience WebCore TU Member
0.5 | 大津谷さん | Project Owner Provides guidance and direction at update meetings
Notes: Set expectations around who you are going to need and what kind of skills they will need to have to pull this off.
Use names if specific people are important (i.e. Billy is the only guy who can do X).

## Slide 10: How big is this thing?
Ship it!
サイトコンセプト策定
画面設計
ビジュアルデザイン
とマークアップ
2 weeks
2 weeks
2 weeks
This is a guess. Not a commitment.
Notes: Give your sponsors some idea of how big this thing is (1, 3, or 6 monther).
Before you can complete this slide you and the team should create and estimate a high-level story list for the project.
This isn’t a commitment (too many unknowns). It’s just a really rough guess. Don’t treat it as anything else.

## Slide 11: Trade-off sliders
 | The classic four
 | Feature completeness (scope)
 | Stay within budget (budget)
 | Deliver project on time (time)
 | High quality, low defects (quality)
ON
OFF
 | Other important things
 | Ease of use
 | Don’t make me think!
 | Detailed audits (log everything)
ON
OFF
ON
OFF
ON
OFF
ON
OFF
ON
OFF
ON
OFF
Notes: When push comes to shove, something has to give. Here we want to be clear on what that is.
On agile projects we flex on scope. But there could be others factors at play here so get ready to listen as you customer tells you which forces can bend (scope) and which are written in stone (usually budget).
Slider rules:
1. No two sliders can occupy the same level.
2. List other important project factors down below.